## Summary
MEMEH UAT Test Plan
Execution dashboard and controlled acceptance gate
Version 2.0 ¦ Issued 2026-07-28 ¦ Source baseline: MEMEH Core Product Document and Concept Note, 2026-07-21
Metric | Value | Acceptance gate
Total test cases | 32 | Production readiness requires: all Critical cases passed; no open Critical or High defects; security, idempotency, route-snapshot, adapter, callback and recovery evidence complete; accountable platform, bank, operations, security, product and compliance approvals recorded.
Passed | 0
Failed | 0
Blocked | 0
Not run | 32
Pass rate | 0%
Product boundary
MEMEH Core is the machine-to-machine Request-to-Pay orchestration runtime. The Enablement Portal governs access, credentials, documentation, UAT, downloads and audit support. Trusted CA/CAS resolves aliases. The runtime Control Plane publishes route snapshots. Bank Adapters and participants own bank/IPS mechanics and authoritative outcomes.

## Test Cases
MEMEH UAT Test Cases
Editable execution register; use filters and controlled status values
Version 2.0 ¦ Issued 2026-07-28 ¦ Source baseline: MEMEH Core Product Document and Concept Note, 2026-07-21
Test ID | Domain | Priority | Component | Requirement | Preconditions | Test Steps | Expected Result | Owner | Environment | Data / Reference | Evidence Link | Execution Date | Status | Defect ID | Actual Result | Notes
CORE-001 | Functional | Critical | Payment-intent API | Accept a valid authenticated request | Active sandbox client and valid aliases | Sign and submit one valid payment intent | Request is accepted once; stable request and instruction identifiers returned | Platform QA | Sandbox |  |  |  | Not Run
CORE-002 | Validation | High | Payment-intent API | Reject a missing required field | Active client | Omit currency and submit | Deterministic validation error identifies currency; no dependency call | Platform QA | Sandbox |  |  |  | Not Run
SEC-001 | Security | Critical | Authentication | Reject invalid request signature | Active client | Alter body after signing | Request rejected; no processing; security event recorded | Security QA | UAT |  |  |  | Not Run
SEC-002 | Security | Critical | Replay protection | Reject nonce reuse | Active client | Reuse nonce within replay window | Second request rejected and auditable | Security QA | UAT |  |  |  | Not Run
IDEM-001 | Idempotency | Critical | Core | Return original outcome for identical replay | First request completed intake | Repeat same key and identical payload | Same logical result; no duplicate instruction or dispatch | Platform QA | UAT |  |  |  | Not Run
IDEM-002 | Idempotency | Critical | Core | Reject changed payload for used key | First request completed intake | Repeat key with changed amount | Conflict returned; original request unchanged | Platform QA | UAT |  |  |  | Not Run
CA-001 | Alias resolution | Critical | CA/CAS | Resolve valid payer and payee aliases | Trusted service available | Submit known valid aliases | Verified addresses and servicer IDs captured | Integration QA | UAT |  |  |  | Not Run
CA-002 | Alias resolution | High | CA/CAS | Fail closed for unknown alias | Trusted service available | Submit unknown payer alias | Categorized rejection; no canonical dispatch | Integration QA | UAT |  |  |  | Not Run
CA-003 | Resilience | High | CA/CAS | Bound timeout behavior | Fault injection enabled | Delay CA/CAS beyond timeout | Bounded failure/retry; trace shows dependency outcome | Resilience QA | UAT |  |  |  | Not Run
ROUTE-001 | Routing | Critical | Runtime Control Plane | Use active versioned snapshot | Approved snapshot published | Submit routable request | Selected snapshot version, participant and adapter recorded | Integration QA | UAT |  |  |  | Not Run
ROUTE-002 | Routing | Critical | Runtime Control Plane | Reject invalid or expired snapshot | Expired snapshot loaded | Submit request | No unapproved fallback; explicit safe failure | Integration QA | UAT |  |  |  | Not Run
INST-001 | Functional | Critical | Canonical instruction | Build a complete deterministic instruction | Aliases resolved | Inspect dispatched instruction | Schema, addresses, amount, currency, reference and context are correct | Bank QA | UAT |  |  |  | Not Run
ADPT-001 | Adapter | Critical | Bank Adapter | Accept canonical instruction once | Adapter available | Dispatch valid instruction | Adapter acceptance recorded with correlation ID | Bank QA | UAT |  |  |  | Not Run
ADPT-002 | Adapter | Critical | Bank Adapter | Prevent duplicate downstream execution | Adapter can detect duplicate instruction | Deliver same instruction twice | One execution; duplicate handled idempotently | Bank QA | UAT |  |  |  | Not Run
ADPT-003 | Resilience | High | Bank Adapter | Retry transient timeout safely | Fault injection enabled | Timeout first attempt, accept retry | Bounded retry with same instruction identity; attempt history complete | Resilience QA | UAT |  |  |  | Not Run
CALL-001 | Callback | Critical | Callback inbox | Accept valid signed callback | Approved callback key | Send valid intermediate and terminal callbacks | Signature valid; states applied; event history complete | Bank QA | UAT |  |  |  | Not Run
CALL-002 | Callback | Critical | Callback inbox | Reject invalid callback signature | Known instruction | Send callback with invalid signature | Rejected; state unchanged; security event recorded | Security QA | UAT |  |  |  | Not Run
CALL-003 | Callback | High | Callback inbox | Deduplicate callback event | First callback accepted | Repeat same event ID | No duplicate state transition or event | Bank QA | UAT |  |  |  | Not Run
CALL-004 | State model | High | Lifecycle | Reject regressive transition | Instruction terminal | Send earlier/intermediate status | Transition rejected and auditable | Core QA | UAT |  |  |  | Not Run
STAT-001 | Visibility | Critical | Status API | Expose current status to owning client | Request has events | Query by request ID | Current authoritative state returned | Platform QA | UAT |  |  |  | Not Run
STAT-002 | Authorization | Critical | Status API | Prevent cross-client access | Two clients exist | Client B queries Client A request | No data disclosure | Security QA | UAT |  |  |  | Not Run
EVT-001 | Auditability | High | Event API | Expose ordered immutable event history | Lifecycle complete | Query events | All accepted events ordered with timestamps and source | Operations QA | UAT |  |  |  | Not Run
PORT-001 | Portal | High | Access application | Submit complete access request | Public user | Complete all required steps and submit | Reference created; admin can review; audit evidence retained | Portal QA | Sandbox |  |  |  | Not Run
PORT-002 | Portal | Critical | Admin authorization | Block non-admin access | Partner account | Request admin route | Access denied without data exposure | Security QA | Sandbox |  |  |  | Not Run
PORT-003 | Portal | High | Partner activation | Use signed expiring invitation | Approved request | Activate once, then retry/expire | Valid activation works once; invalid/expired links fail safely | Portal QA | Sandbox |  |  |  | Not Run
PORT-004 | Portal | High | Credentials | Protect sandbox secret | Partner account | View and store credential per policy | Secret access is authorized, encrypted at rest, and audited | Security QA | Sandbox |  |  |  | Not Run
PORT-005 | Portal | Medium | Downloads | Enforce artifact visibility | Public and partner artifacts | Access each with public/partner user | Only authorized active artifacts are delivered | Portal QA | Sandbox |  |  |  | Not Run
OPS-001 | Operations | Critical | End-to-end trace | Reconstruct the full request lifecycle | Completed request | Trace by platform reference | Validation, resolution, snapshot, route, attempts, callbacks and terminal state found | Operations | UAT |  |  |  | Not Run
OPS-002 | Recovery | High | Reconciliation | Recover a missing callback safely | Callback delayed/lost in test | Reconcile adapter and Core state | Outcome reconciled without fabricated payment success; evidence recorded | Operations | UAT |  |  |  | Not Run
PERF-001 | Performance | High | Core | Meet approved intake and dispatch latency | Representative load profile | Run load test at target concurrency | p50/p95/p99 meet approved SLO; no error or saturation breach | Performance QA | UAT |  |  |  | Not Run
DR-001 | Recovery | Critical | Data platform | Restore authoritative records | Approved backup | Perform restoration exercise | RPO/RTO met; integrity and event order verified | Operations | DR |  |  |  | Not Run
OWASP-001 | Security | Critical | Portal/Core | Pass critical OWASP negative tests | Test environment | Run authorization, injection, SSRF, integrity and logging cases | No critical/high exploitable finding remains | Security QA | UAT |  |  |  | Not Run

## Execution Evidence
Execution Evidence Register
Attach reproducible evidence without storing secrets or unmasked sensitive data
Version 2.0 ¦ Issued 2026-07-28 ¦ Source baseline: MEMEH Core Product Document and Concept Note, 2026-07-21
Evidence ID | Test ID | Executed By | Execution Time | Environment | Request ID | Instruction ID | Route Snapshot | Artifact / URL | Redaction Checked | Notes

## Defects
Defect Register
Track severity, ownership, treatment, retest and closure
Version 2.0 ¦ Issued 2026-07-28 ¦ Source baseline: MEMEH Core Product Document and Concept Note, 2026-07-21
Defect ID | Test ID | Title | Severity | Status | Owner | Opened | Target | Root Cause | Treatment / Fix | Retest Evidence | Risk Acceptance

## Sign-off
Production Readiness Sign-off
All decisions must be attributable and supported by evidence
Version 2.0 ¦ Issued 2026-07-28 ¦ Source baseline: MEMEH Core Product Document and Concept Note, 2026-07-21
Role | Name | Organization | Decision | Conditions | Evidence Reference | Date | Signature / Approval ID
Payment platform |  |  | Pending
Participating bank / Adapter |  |  | Pending
MEMEH Operations |  |  | Pending
Security |  |  | Pending
Product Owner |  |  | Pending
Risk and Compliance |  |  | Pending

## Lists
Status | Priority | Environment | Decision
Not Run | Critical | Sandbox | Pending
Pass | High | UAT | Approve
Fail | Medium | DR | Reject
Blocked | Low | Production Verification | Approve with Conditions
N/A
Controlled values; do not delete without updating validations.